## Sheet 1
Table 1
Store Opening Timeline
input your store details
Target Soft Opening Date
Opening
Month |  | Month | Notes
FUNDING & SPACE
Finalize funding
Identify suitable spaces
Negotiate lease for space you select
Sign lease
Design Space
Begin build-out (except lighting)
ADMINISTRATIVE
Incorporate the Business
File for Business License, Sales Tax Cert., etc.
Apply for business credit card
Open Bank Accounts
Apply for SAN (from Bowker)
Create Credit Reference Sheet
Set up chart of accounts on accounting software
Hire bookkeeping/payroll services
Select/install security systems
Purchase POS/inventory system and hardware |  |  | Buy one terminal early on to begin creating purchase orders for non-book merchandise
Open Credit Card Processing Account
STORE DESIGN
Order custom fixtures per plan |  |  | Confirm turn-around time with fixture vendor
install lighting per plan |  |  | Install after store layout is complete
Create planogram |  |  | Using fixture layout, designate sections and order quantities
Order display accessories
MARKETING
Develop logo design/branding
Website design/set up indiecommerce
Refine marketing plan
Establish social media accounts & post progress
Network in community |  |  | Schools, non-profits, etc
BUYING INITIAL INVENTORY
Request title databases |  |  | From book wholesaler & Above the Treeline
Learn Edelweiss for publisher catalogs |  |  | Sign up for free account at edelweiss.com
Open accounts with key publishers |  |  | Keep this simple for now, you’ll open more accounts later
Develop initial book inventory order |  |  | Using title databases and planogram, create your own master order
Develop front list orders |  |  | Add new books to your master order spreadsheet
Submit vendor new account applications for non-book vendors |  |  | Check with vendor for specific instructions. You may place your first order with the store credit card, but state delivery dates (so you don’t have merchandise arriving before you have your certificate of occupancy).
STAFFING & TRAINING
Recruit staff
Develop staff schedule
Train staff |  |  | Merchandising, POS, title searches, customer service
STORE SET-UP
Receive & price non-book items
Receive & merchandise books
Withdraw funds for cash drawers
Soft opening
Grand opening (2-4 weeks after soft opening)